Project B for K product

Intelligent Quality Operation Monitoring

Statement of Work (SOW)

| Project Full Name | Project B for K Product — Intelligent Quality Operation Monitoring |
| --- | --- |
| Project Abbreviation | Kronos - ProjectB |
| Deployment Location | B08-2F |
| Document Date | March 2026 |
| Party A (User) | Fulian-B09-4F-ME(Kronos) |
| Party B (Vendor) | Fulian-B09-4F-IIC-AI |

This document is intended for project scope confirmation, technical feasibility, resource estimation, and phased delivery definition.

# Revision History

| No. | Date | Department | Author | Version | Details |
| --- | --- | --- | --- | --- | --- |
| 1 | 2026/03 | FULIAN-B09-4F-IIC-AI | Ruan Wen Long | V1.0 | Initial version — SOW organized for Project B / K-IOM |

# Review Sign-Off

Please reference the Esign system for review sign-off records.

Contents

Revision History	2

Review Sign-Off	2

1  Project Overview	4

1.1  Project Abbreviation	4

1.2  Project Background	4

1.3  Project Objectives	4

2  Project Scope	5

2.1  Implementation Service Scope	5

2.2  Organizational Scope	5

2.3  Business Scope	5

3  Project Objectives & Detection Scenarios	6

3.1  Monitoring Objectives	6

3.2  Core Detection Scenario & Action Scope	6

3.3  Software Features	7

3.4  Supplementary Project Information	7

3.4.1  Data & Collection Notes	7

3.4.2  System Server & Hardware Requirements	8

4  Development Schedule & Resource Assessment	9

4.1  Overall Development Timeline & Milestones	9

4.2  Manpower Allocation Recommendations	10

4.3  Notes on Resource Investment Boundaries	10

5  Project Organization & Staffing	11

6  Project Risks & Countermeasures	12

7  Acceptance Criteria & Plan Deliverables	13

8  Project Management	15

8.1  Project Assurance & Staffing	15

8.2  Project Change Control	15

9  Training	15

10  After-Sales Service & Notes	16

Appendix: Summary of CPEG AI Software Development & Delivery Regulations	17

# 1  Project Overview

## 1.1  Project Abbreviation

| Field | Details |
| --- | --- |
| Project Full Name | Project B for K Product — Intelligent Operation Monitoring |
| Project Abbreviation | Kronos – Project B |
| Deployment Location | B08-2F |
| Party A (User) | Fulian-B09-4F-ME(Kronos) |
| Party B (Vendor) | Fulian-B09-4F-IIC-AI |

## 1.2  Project Background

Project B for K Product is an AI-powered intelligent operation monitoring initiative deployed at Building B08, Floor 2F to meet the customer's requirement for strict process control and to ensure that the product meets quality standards.

The project is designed based on the customer's need for automated and reliable monitoring, leveraging computer vision and AI algorithms to verify that packaging operations on the production line are performed correctly and consistently to satisfy customer quality requirements.

The system is designed to ensure that operators follow standardized procedures when packaging K products, including correct component placement in boxes, barcode scanning verification for all components of the same type, and complete label affixing on finished packages. This initiative directly supports quality control, traceability, and operational compliance on the production floor.

This document formalizes the project scope into a SOW structure for requirements confirmation, project approval, and subsequent implementation alignment.

## 1.3  Project Objectives

- Deploy and validate an AI vision monitoring system at B08-2F covering packaging operation compliance for K product.

- Automate real-time detection of packaging actions, including: component placement in box, barcode scanning verification (all same-type components), and label affixing completeness.

- Achieve phased accuracy improvement: 80% (Phase 1) → 90% (Phase 2) → 95% (Phase 3).

- Ensure automated event logging and alert generation for non-conforming operations.

- Provide the basis for Esign approval, hardware preparation, development execution, and formal acceptance.

# 2  Project Scope

## 2.1  Implementation Service Scope

Party B shall provide the following services throughout the Product Kronos lifecycle:

- Requirements clarification and technical feasibility analysis for all packaging operation detection scenarios at B08-2F.

- AI algorithm development for computer vision detection including action recognition, barcode scan verification, and label completeness checking.

- IP camera configuration and network setup for the deployment location.

- PC server environment setup, system deployment, and integration.

- On-site deployment and testing with documented test results and feedback scores.

- Trial run optimization, user onboarding, and knowledge transfer to the OT team.

- Project management, milestone tracking, and risk escalation throughout the delivery period.

If the project scope is extended (e.g., additional production lines, new detection scenarios), the implementation scope shall be adjusted through the formal change control process. The specific scope shall be subject to requirements or commercial documents signed off by both parties.

## 2.2  Organizational Scope

Party A and Party B shall communicate through meetings, email, and instant messaging tools, and shall conduct weekly meetings or dedicated meetings aligned with the project cadence to track requirements, risks, plans, and issue closure.

Party A (FULIAN-B09-4F ME Kronos) shall organize resource coordination, on-site contacts, hardware procurement follow-up, and business-rule confirmation. Party B (FULIAN-B09-4F-IIC-AI) shall be responsible for algorithm development, deployment, and deliverable document preparation.

## 2.3  Business Scope

- This project primarily covers AI-based visual monitoring for packaging operation compliance on the K product line at B08-2F.

- This project does not include formal interface development with peripheral systems such as MES, ERP, or BBS unless explicitly specified in a frozen requirements version.

- This project does not include automatic equipment control, mechanical linkage, or closed-loop process-control functions.

- Any new detection scenario, additional production line, new interface, or changed accuracy target introduced after scope freeze shall be evaluated through change control and may affect schedule, cost, and acceptance criteria.

- The software includes a standard user interface (UI) that supports all functions defined in this SOW.If a customized UI is requested, each customized version will be treated as a separate development item and will require an additional fee equal to 30% of the total software development cost per version.

- Customized UI development and acceptance shall be handled separately and shall not affect the acceptance, delivery schedule, or payment milestones of the standard software functions specified in this SOW.

# 3  Project Objectives & Detection Scenarios

## 3.1  Monitoring Objectives

Build and validate an AI vision monitoring solution for the K product packaging line at B08-2F to automatically detect operational non-compliance, missing components, barcode scan omissions, and label affixing errors. The system shall provide real-time alerts and automated event logging to support quality management, compliance reporting, and continuous process improvement.

## 3.2  Core Detection Scenario & Action Scope

This project covers one deployment scenario at B08-2F with three core monitored actions:

| No. | Location | Scenario | Monitored Action | Description | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | B08-2F Packaging Line | Intelligent Packaging Operation Monitoring | Component Placement | Verify correct placement of all components inside the box as per SOP | In Scope |
| 2 |  |  | Barcode Scan Verification | Verify all same-type components are scanned before sealing | In Scope |
| 3 |  |  | Label Affixing Completeness | Detect whether all required labels are correctly affixed on the finished package | In Scope |

## 3.3  Software Features

Core Software Capabilities:

(1) The system operates continuously and does not require manual interaction from operators for standard monitoring functions.

(2) Automatically records detailed event history for each packaging operation and detection item.

(3) Event history is stored by day and by month, with data logs retained for at least 3 months.

(4) The system automatically pauses monitoring when no activity is detected at the workstation.

(5) When a warning alarm is triggered, the assigned personnel can immediately view the alert type on the monitoring interface.

Worker / Operator Compliance Requirements:

(1) Workers must perform packaging tasks in accordance with the software system SOP.

(2) Any action that blocks or obstructs the camera view will affect the monitoring result and be recorded as an anomaly.

(3) When a warning alarm is triggered, the identified non-compliance must be corrected before proceeding.

(4) Intentional bypass of alerts will be recorded in the event history log.

## 3.4  Supplementary Project Information

## 3.4.1  Data & Collection Notes

Training and validation data for all detection scenarios shall be sourced from fixed on-site IP cameras installed at the B08-2F packaging workstation. Data collection shall cover multiple operators, shifts, lighting conditions, and packaging configurations to ensure model robustness. No independent data collection system build is required; existing camera infrastructure is used.

## 3.4.2  System Server & Hardware Requirements

| No. | Category | Recommended Configuration | Details |
| --- | --- | --- | --- |
| 1 | AI Edge Server PC | CPU: Intel Core i5 ¦ GPU: NVIDIA RTX ¦ SSD: 1TB ¦ PSU: 550W ¦ HDD: 4TB | 1 outdoor unit deployed across B08-2F. System installation completed by IT; environment setup by AI team. |
| 2 | GPU Development Workstation | i9 13th Gen / RAM 64GB / RTX 4090 | Used for algorithm development, debugging, and model training. |
| 3 | IP Camera | Camera ip 8mp kbvision KX-CAiF8003N-DL-AB | Camera positions to be confirmed by AI team at B08-2F packaging line. |
| 4 | Mount / Installation Fixture | Designed per physical size & resolution | Ensures viewing angle, stability, and maintenance accessibility for each deployment location. |

Note: Specific hardware configurations shall be finalized based on the user's Esign-confirmed requirements.

Party B provides one-time reference hardware specifications. If procurement cannot be completed due to stock availability, brand policy, or pricing, Party A shall source equivalent or higher-performance models.

This document does not independently commit to source-code disclosure, external system interfaces, or formal warranty / maintenance terms.

# 4  Development Schedule & Resource Assessment

## 4.1  Overall Development Timeline & Milestones

The following milestone plan reflects the project execution schedule. Development is tracked against the Esign-approved project registration date and hardware availability.

| Phase/Milestones | Main Work | Deliverables | Acceptance Criteria | Timeline |
| --- | --- | --- | --- | --- |
| Initiation | Clarify project boundaries, resources, and milestones | SOW (requirements confirmation, implementation plan) | Documents delivered and signed off in Esign | 1 month |
| Assessment / PoC | Complete demo system for the scenario | Initial test report, issue list, demo system | System demo demonstrates basic detection function for scenario | 1 month |
| Optimization | Complete accuracy optimization and on-site validation | Optimization records, deployment recommendations | Detection accuracy meets agreed thresholds; on-site validation completed | 1 month |
| Project Closure/ Transition | Deploy software to production; complete trial run and user onboarding | Final detail report (SOP, scope & change recommendations) | Complete product handover to production line; written confirmation submitted to Esign | 1 month |

Note: Please refer to Chapter 7 Acceptance Criteria & Plan Deliverables and the default option.

## 4.2  Manpower Allocation Recommendations

| No. | Role | Headcount | Main Responsibilities | Remarks |
| --- | --- | --- | --- | --- |
| 1 | AI Project Manager | 1 | Overall project schedule, milestone tracking & cross-team coordination | Core role |
| 2 | AI Software Development Engineer | 1 | Model training, testing, and performance validation | Core role |
| 3 | AI Data Engineer | 1 | Data labeling for packaging action and barcode scenarios | Core role |
| 4 | AI Deployment Engineer | 1 | Camera network configuration & Edge AI server deployment | Core role |
| 5 | AI Algorithm Engineer | 1 | Algorithm optimization and accuracy improvement | Extended role |
| 6 | AI Alogorithm Manager | 1 | Solution management and patent coordination | Extended role |
| 7 | AI Director | 1 | Overal project governance and escalation management | Management role |

A total team size of 7 personnel is recommended. Personnel charges shall be calculated from the date Esign approval (or expense-transfer commitment approval) is completed and, in principle, settled monthly. If payment becomes due but remains unpaid, Party B may suspend the provision of corresponding manpower resources, and any schedule loss caused thereby shall be borne by Party A.

## 4.3  Notes on Resource Investment Boundaries

- The current schedule estimate is based on existing requirements and confirmed camera scenarios at B08-2F. If new scenarios are added, site conditions change, or accuracy thresholds are raised, the schedule and resources shall be adjusted accordingly.

- Hardware specifications recommended by Party B are for reference only. Brand, procurement channel, and policy compliance shall be determined by Party A.

- High detection accuracy cannot be achieved by extending development time alone. It also depends on camera stability, sample quality, environmental consistency, and continuous annotation optimization.

- Additional deployment time may be required for hardware received after the initial schedule date.

# 5  Project Organization & Staffing

It is recommended that this project adopt a coordinated model with four role categories: (1) Project Management, (2) Algorithm Development, (3) Data Annotation, and (4) Deployment & Implementation. The detailed responsibilities for each role are as follows:

| Role Category | Responsibilities | Key Personnel |
| --- | --- | --- |
| Project Management | Milestone progression, risk management, stakeholder communication, and Esign case management. | AI PM; AI Director |
| Algorithm Development | AI model development for all detection scenarios including packaging action recognition, barcode verification, and label detection. | AI Software Engineer; AI Algorithm Engineer |
| Data Processing | Video/image data labeling for all detection scenarios, ensuring label quality for training and validation datasets. | Data Engineer |
| Deployment & Implementation | On-site IP camera configuration, PC server deployment, system integration testing, and trial run support. | AI Deployment Engineer; OT Owner (TBD) |

Before formal project kickoff, it is recommended that both parties define the project contacts, approval path, requirements approvers, and acceptance owners in order to reduce schedule risks caused by later organizational changes.

# 6  Project Risks & Countermeasures

| No. | Risk / Trigger | Countermeasure / Responsibility |
| --- | --- | --- |
| 1 | Promised hardware (PC, camera) not provided on time by Party A | Party A is responsible for hardware procurement. If delayed, Party A shall bear the resulting extension manpower cost at not lower than USD 4,000/person/month during the delay period. |
| 2 | Party A does not issue written acceptance within 1 month of qualified delivery | The extension period shall be treated as user-side delay. Party A shall bear extension manpower cost unless both parties agree otherwise in writing. |
| 3 | Party A provides only verbal rejection or unclear feedback | Verbal feedback without written nonconformance evidence in Esign shall not constitute formal rejection. Party A must provide written defect evidence or nonconformance records. |
| 4 | Late scope additions or production line changes after scope freeze | Any new scenario, additional line, or changed accuracy target shall be evaluated through change control and may affect schedule, cost, and acceptance criteria. |
| 5 | Camera accessibility issues or hardware repair delays at B08-2F | Camera accessibility shall be confirmed by the AI team prior to development. Cameras requiring repair must be completed before associated scenarios are scheduled. |
| 6 | Delayed payment or internal process approval | If approval, payment, or internal process completion is delayed, Party B may adjust manpower input and milestone dates after issuing a risk notice. |

# 7  Acceptance Criteria & Plan Deliverables

This project adopts phased acceptance. Each phase shall primarily use electronic deliverables, and phase completion shall be based on signatures or email confirmation from both parties. The formally frozen version shall prevail for UAT and production acceptance.

| No. | Phase Target | Estimated Duration | Total Cost (USD) | Notes |
| --- | --- | --- | --- | --- |
| 1 | Approx. 70% accuracy | 1 months | $3,000 | Deliver the first runnable version to verify basic recognition capability |
| 2 | Approx. 90% accuracy | 2 months | $7,000 | Enter the higher-accuracy stage, relying on more valid samples & continuous optimization |
| 3 | Approx. 99% accuracy | 3 months | $9,000 | High-precision target stage, requiring high data quality, on-site consistency, & optimization resources |

Calculate accuracy:

Accuracy=Number of correct packing inspections by AITotal number of packing inspections *100%

Explanation:

- Correct packaging inspections by AI: number of times the AI system correctly verifies the product packaging operation.

- Total packaging inspections: total number of packaging inspection attempts during testing.

- Accuracy (%): represents the ratio of correct inspections performed by the AI system over the total number of inspections.

- The system accuracy will be improved gradually during the project phases, with target values of approximately 70%, 90%, and 99%.

Note: The default option is No. 2

| Phase | Main Work | Deliverables | Acceptance Criteria | Payment |
| --- | --- | --- | --- | --- |
| Initiation | Clarify project boundaries, resources, and milestones | SOW (requirements confirmation, implementation plan) | Documents delivered and signed off in Esign | 30% of the project price |
| Assessment / PoC | Complete demo system for all 3 scenarios; achieve ~70% accuracy | Initial test report, issue list, demo system | System demo demonstrates basic detection for each scenario | 30% of the project price |
| Optimization (~90%) | Complete accuracy optimization and on-site validation | Optimization records, deployment recommendations | Detection accuracy meets 90% threshold; on-site validation completed | 30% of the project price |
| Project Closure (~99%) | Deploy to production; complete trial run and user onboarding | Final detail report (SOP, scope & change recommendations) | Complete handover to production line; written confirmation in Esign | 10% of the project price |

Scenario-Level Feedback Thresholds:

Each deployed scenario is evaluated against a feedback score (Phase 1: ≥80%; Phase 2: ≥90%; Phase 3: ≥95%).

Scenarios scoring below the threshold during trial run must be optimized before final acceptance.

# 8  Project Management

## 8.1  Project Assurance & Staffing

Before project kickoff, Party B shall clarify the key roles participating in the project and their responsibilities, while Party A shall clarify the business contact, on-site contact, and acceptance contact. During project implementation, any change to key roles or scope shall be handled in accordance with the change control process.

For delays caused by factors beyond Party B's control — including but not limited to delayed hardware procurement, delayed sample provision, lack of on-site resource cooperation, and delayed approval processes on Party A's side — Party B shall not bear the resulting schedule responsibility, but shall promptly raise the risk and assist in evaluating the impact.

## 8.2  Project Change Control

If any content agreed in this SOW needs to be changed, the proposing party shall initiate a change request specifying the change content, reason, and the impact on scope, schedule, resources, cost, and quality. Changes may only be implemented after evaluation by both project managers and confirmation by authorized representatives. Unconfirmed new requirements shall not be included in this delivery and acceptance.

# 9  Training

Party B shall provide necessary training to relevant personnel of Party A during the Implementation & User Onboarding phase. Training shall cover:

- System operation and monitoring interface usage for on-site operators and supervisors.

- Alert response procedures — how to interpret alarm types and corrective action steps.

- Camera and server basic maintenance awareness for the on-site IT/OT team.

- SOP compliance requirements aligned with the software system's operating standards.

- Escalation paths for system anomalies or detection accuracy issues during the trial run period.

Training materials including SOPs, user guides, and quick-reference cards shall be delivered as part of the final deliverable package and submitted to the Esign system upon project closure.

# 10  After-Sales Service & Notes

This document is organized based on the Project B for K Product project materials and is primarily used to define the implementation scope, delivery milestones, and subsequent development recommendations. It does not independently constitute a formal commercial quotation, final performance commitment, or maintenance contract.

If additional detection scenarios or system extensions are required following project closure, the after-sales service scope, term, response level, and fee arrangement shall be separately defined by both parties in a contract, PO, or supplementary agreement.

During the current implementation and preparation stage, it is recommended that both parties at least agree on the following:

- Issue feedback contact and response timeline for post-deployment anomalies.

- Regular meeting cadence for trial run monitoring and optimization tracking.

- Stage review checkpoints aligned with milestone dates.

- Escalation path for key risks impacting system stability or detection accuracy.

# Appendix: Summary of CPEG AI Software Development & Delivery Regulations

The following regulations govern all AI software development and delivery activities under the CPEG framework and apply to this project:

- Quick Response to Customer Needs & Charging: When customers have urgent AI needs but requirements are not yet clear, the customer or PM may propose human support fees in Esign. The customer must commit in writing to pay the AI human support fee at USD 4,000/person/month from the Esign case registration date until case completion.

- Minimum Price for a Single Software: The minimum price for any single software deliverable is generally not less than USD 6,000.

- Esign Requirements: All AI projects in 2026 must be signed by Esign as PO evidence, attached to the SOW. Hardware specifications, development schedule, manpower investment, and acceptance criteria must be clearly stated in Esign.

- Delay Countermeasures: If Party A fails to provide promised hardware on time, or fails to submit written acceptance in Esign within one month from the delivery date, Party A must bear the developer's labor costs at not less than USD 4,000/person/month for the extension period.

- Software Development Cycle: The standard development cycle from case registration to completion shall not exceed 3 months. Projects exceeding 3 months must be split into multiple deliverables with separate quotations. Expedited development requires a surcharge of 50%–200%.

- Regarding Benefits of Software Usage: Users should fully evaluate the benefits before registering an AI project. Since the developer has no control over how users apply the software, refusal to pay development fees on the grounds of poor results constitutes a breach of contract.

Note: This SOW has been organized based on Project B for K Product requirements and packaging line monitoring scenarios.

For items not provided in the original materials — such as detailed Party A/B entity information, formal commercial quotation, ROI analysis, or warranty/maintenance levels — this document uniformly uses 'TBD' or 'to be agreed separately' to avoid introducing unconfirmed information.

All final commitments are subject to the formally signed Esign-approved version of this SOW.